## Labor Estimator
Barrett Plumbing - Labor Hours Estimator
Enter fixture counts in BLUE cells. Formulas calculate totals automatically.
Job Name / Address:
UNDERGROUND PLUMBING
Item | Count | Hrs/Each | Total Hrs | Phase Total | Notes
Base Underground Hours |  | 16 | 16 |  | Minimum hours for any underground job (main line, water service, etc.)
Toilet (drain rough-in) | 3 | 1.5 | 4.5 |  | Per toilet drain run from main
Shower/Tub (drain rough-in) | 2 | 2 | 4 |  | Per shower or tub drain
Sink/Lavatory (drain rough-in) | 4 | 1 | 4 |  | Per sink drain run
Kitchen (drain + vent rough-in) | 1 | 2.5 | 2.5 |  | Kitchen drain, dishwasher, disposal
Laundry (drain rough-in) | 1 | 1.5 | 1.5 |  | Washer drain and vent
Floor Drain / Crock | 1 | 2 | 2 |  | Sump or sewage crock
Backwater Valve | 1 | 1 | 1 |  | Per backwater valve installed
Water Service Entry | 1 | 3 | 3 |  | Main water line into building
Underground Labor Hours |  |  | 38.5 | 38.5
Days (2 people, 8 hrs/day) |  |  | 3 |  | Rounded up to whole days
Mobilization Hours (1 hr/person/day) |  |  | 6 | 6 | 2 people x days = mobilization hours
ROUGH-IN PLUMBING
Item | Count | Hrs/Each | Total Hrs | Phase Total | Notes
Base Rough-In Hours |  | 12 | 12 |  | Main stack, venting, water distribution trunk lines
Toilet (supply + vent rough-in) | 3 | 1.5 | 4.5 |  | PEX supply, vent tie-in per toilet
Shower (supply rough-in) | 1 | 3 | 3 |  | Hot/cold PEX, valve, shower arm stub
Tub/Shower (supply rough-in) | 1 | 3.5 | 3.5 |  | Hot/cold PEX, valve, tub spout + shower stub
Sink/Lavatory (supply rough-in) | 4 | 1.5 | 6 |  | Hot/cold PEX supply per sink
Kitchen (supply rough-in) | 1 | 2 | 2 |  | Hot/cold, dishwasher supply, disposal rough
Laundry Box | 1 | 1.5 | 1.5 |  | Washing machine box with hammer arrestors
Ice Maker Box | 1 | 0.5 | 0.5 |  | Ice maker outlet box
Outside Faucet | 2 | 1.5 | 3 |  | Frost-free wall faucet per location
Water Heater (supply rough-in) | 1 | 2 | 2 |  | Copper/ProPress to and from WH location
Rough-In Labor Hours |  |  | 38 | 38
Days (2 people, 8 hrs/day) |  |  | 3 |  | Rounded up to whole days
Mobilization Hours (1 hr/person/day) |  |  | 6 | 6 | 2 people x days = mobilization hours
FINISH PLUMBING
Item | Count | Hrs/Each | Total Hrs | Phase Total | Notes
Base Finish Hours |  | 8 | 8 |  | General setup, testing, pressure test, inspection prep
Toilet (set & connect) | 3 | 1.5 | 4.5 |  | Set toilet, wax ring, supply, caulk
Shower (trim & connect) | 1 | 2.5 | 2.5 |  | Install shower unit, trim, drain, test
Tub/Shower (trim & connect) | 1 | 3 | 3 |  | Install tub/shower, trim, waste & overflow, test
Sink/Lavatory (set & connect) | 4 | 1.5 | 6 |  | Mount sink, faucet, supply lines, P-trap, drain
Kitchen Sink (set & connect) | 1 | 2.5 | 2.5 |  | Mount sink, faucet, disposal, supplies, drain
Garbage Disposal (install) | 1 | 0.5 | 0.5 |  | Connect disposal to sink drain
Water Heater (install & connect) | 1 | 4 | 4 |  | Set WH, connect gas/elec, piping, pan, T&P tube
Outside Faucet (finish) | 2 | 0.5 | 1 |  | Install handle, trim, test
Washing Machine Box (connect) | 1 | 0.5 | 0.5 |  | Connect supplies and test
Ice Maker Box (connect) | 1 | 0.25 | 0.25 |  | Connect supply and test
Finish Labor Hours |  |  | 32.75 | 32.75
Days (2 people, 8 hrs/day) |  |  | 3 |  | Rounded up to whole days
Mobilization Hours (1 hr/person/day) |  |  | 6 | 6 | 2 people x days = mobilization hours
JOB SUMMARY
Phase |  |  | Labor Hrs | Mob Hrs | Total Hrs
Underground |  |  | 38.5 | 6 | 44.5
Rough-In |  |  | 38 | 6 | 44
Finish |  |  | 32.75 | 6 | 38.75
TOTAL |  |  | 109.25 | 18 | 127.25